## Sheet1
| Back-End | Front-End |  | Back-End | Front-End
Web Design |  | 16 |  |  | 16
Initial DB Design | 16 |  |  | 24
Authentication | 8 | 8 |  | 8 | 8
Search | 8 | 16 |  | 16 | 16
List | 16 | 16 |  | 24 | 24
Filter | 16 | 16 |  | 16 | 16
Details | 16 | 20 |  | 16 | 20
Book review | 8 | 16 |  | 8 | 16
Pay | 30 | 16 |  | 48 | 24
Confirmation |  | 4 |  |  | 4
Managment
Profile | 8 | 8 |  | 8 | 8
Listings
List | 8 | 8 |  | 8 | 8
Add/Update | 20 | 20 |  | 24 | 24
Delete | 4 | 4 |  | 4 | 4
Bookings
List | 8 | 8 |  | 8 | 8
Update | 8 | 8 |  | 8 | 8
Add Payments | 16 | 16 |  | 16 | 16
Cancel/Refund? | 16 | 8 |  | 16 | 8
Deployment | 40 |  |  | 40
QA | 20 |  |  | 16
bugs fixing | 30 |  |  | 20
|  | Niurka Estimation |  |  |  | Ramon Estimation
|  |  |  | 1wk=20h | 1m=4wk |  |  |  | 1wk=20h | 1m=4wk
| 296 | 208 | 504 | 25.2 | 6.3 | 328 | 228 | 556 | 27.8 | 6.95
|  |  | 25200 |  |  |  |  | 25020